## Sheet1
|  |  | Art | Amount | Time est. |  | Animation | Amount | Time est. |  | LD | Amount | Time est. |  | GD | Amount | Time est. |  | Sound | Amount | Time est. |  | Code | Amount | Time est.
total cost | 270833.3333 | cost |  |  |  | 92083.3333 |  |  |  | 36250 |  |  |  | 14583.3333 |  |  |  | 10416.6667 |  |  |  | 17777.7778 |  |  |  | 52083.3333
buffer | 30000 | Total |  |  | 221 |  |  |  | 87 |  |  |  | 35 |  |  |  | 25 |  |  |  | 80 |  |  |  | 125
|  |  | world dressing | 1x1km² |  |  | characters | 20x | 15 |  | world layout | 3x | 5 |  | weapon balancing | 1x | 10 |  | background music | 1x | 5 |  | character movement | 1x | 4
costs: |  |  | forest | 1x | 2 |  | hivemind | 20x | 15 |  | loot destribution | 2x | 30 |  | hivemind balancing | 1x | 10 |  | weapon sounds | 20x | 20 |  | character interaction | 1x | 6
man month | 7500 |  | farm | 1x | 3 |  | vehicles | 3x | 2 | [5 empty] | dome balancing | 1x | 5 |  | explosion sounds | 5x | 10 |  | character weapons | 1x | 15
|  |  | military base | 1x | 5 |  | animals | 10x | 15 | [9 empty] | hivemind sounds | 20x | 10 |  | hivemind movement | 1x | 4
art outsourcing | 3500 |  | crash site | 1x | 10 |  | weapons | 10x | 10 | [9 empty] | character sounds | 20x | 10 |  | hivemind interaction | 1x | 6
sound outsourcing | 4000 |  | roads | 1x | 2 | [13 empty] | environmental sounds | 50x | 25 |  | hivemind weapons | 1x | 15
|  |  | mountains | 1x | 2 |  | animation graphs | 20x | 30
|  |  | town | 1x | 10 | [17 empty] | animal AI | 1x | 10
18 days per month |  |  | lake | 1x | 1
|  |  | dome | 1x | 1 | [17 empty] | networking | 1x | 30
|  |  | etc. |  | 20
[23 empty] | art tech | 1x | 10
|  |  | shaders | 1x | 10
|  |  | vfx | 50x | 50 | [17 empty] | UI tech | 1x | 20
|  |  | characters | 1x | 15 | [17 empty] | dome | 1x | 5
|  |  | hiveminds | 1x | 15
|  |  | items | 20x | 20
|  |  | rocks | 15x | 15
|  |  | flora | 20x | 20
|  |  | weapons | 10x | 20
|  | cost |  |  |  | 47638.8889
|  | Total |  |  | 245
|  |  | animals | 3x | 50
|  |  | buildings | 4x | 40
|  |  | character attachments | 10x | 25
|  |  | hivemind attachments | 10x | 25
|  |  | environment objects | 30x | 60
|  |  | vehicles | 3x | 45